项目变更申请表Project Change Application Form

| 基本情况 Basic information |  |  |  |
| --- | --- | --- | --- |
| 项目名称 Project name | APC – END TO END Decision Making System |  |  |
| 申请人 Applicant | G.MANOHAR | 申请日期 Application date | 2025/05/24 |

| 请求变更信息 Project change information |  |
| --- | --- |
| - 申请变更的内容 Change content | Material Availability and Planning Schedule Suggestions Function |
| 2.申请变更的原因 Change reasons | Requirement From Adidas Team |
| 3.其他说明 Other remarks |  |

| 变更的影响分析 Impacts assessment |  |  |  |
| --- | --- | --- | --- |
| 1.受影响的基准计划（标注√） Mark √for impacted items | 范围计划 (Scope) | 进度计划 (Schedule) | 成本计划 (Cost) |
|  | Yes | yes | yes |
| 2.具体影响分析 Impacts details |  |  |  |
| 对范围的影响 Impact on scope | Yes (The scope of the project now includes Material Availability and Planning schedule suggestion functions. These additions represent an expansion beyond the original deliverables defined in the project scope. ) |  |  |
| 对进度的影响 Impact on schedule | Milestone; old date; New date. UAT; 2025/06/24; 2025/07/26. GRR; 2025/07/07; 2025/08/09. Go-Live; 2025/07/11; 2025/08/13. Project Exit; 2025/07/28; 2025/08/30. |
| 对成本的影响 Impact on cost | IT Man days will impact Old MD’s: 204 New man days: 224。 The project cost increase 227.96 USD |  |  |
| 其他影响 Other impacts |  |  |  |
| 3.若不进行变更有什么影响？What are the impacts if no changes are made? |  |  |  |

| 审批结果 Approval results |  |  |
| --- | --- | --- |
| 审批意见 Comments | 审批人签字 Sign-off | 审批日期 Date |