## Slide 1: APACHE APC MES End To End Decision Making System
e万行动，e-Apache, one Apache

## Slide 2: 目录 Content
2
项目规划 Project Schedule
1
项目范围 Project Scope
3
项目团队Project Team
5
项目沟通-工具 Project Communication- Tools
6
项目沟通 Project Communication
4
项目组织 Project Organization

## Slide 3: 项目范围 Project Scope
序号 No. | 类别 Category | 范围内 Scope-in | 范围外 Scope-out | 备注 Remark
1 | 系统系统System | 1 . The End-to-End Decision Making System project offers by visualizing data across various stages, We can easily track the status of each PO from order receipt to final shipment enhances the clarity of operational insights but also enables the proactive identification and resolution of process issues . Additionally it ensures stability ,efficiency and sustainability | - | 
2 | 平台 Platform | MES (customized function) | MES | 
3 | 区域 Region | APC | - | 

## Slide 4: 项目规划 Project Schedule
Close
完成
Delay
延迟
On-going
进行中
Not start
未开始
We are here
07/11 Go-live
01/21 PI
07/11 Go-live
PI
01/21 Completed
07/09 User training
蓝图Blueprint
02/05 Not Start
02/05 KO & Blueprint Review
07/10 Project sign-off
06/25 Project sign-off
KO Prep
01/22 Completed
01/22 Kick-off
01/18
01/20
06/24
01/21
01/22
02/05
05/31
GRR：2024/07/07
Not start
06/02
Project Exit：2025/07/28
Realization ：2025/06/24 Not start
03/15
04/10
05/01
06/24

## Slide 5: 项目团队Project Team
Manohar-g
Project Manager
Project Development Team
Manohar-g , S.Premika
Support Team
Chandra-k, Ramaiah-b , Siva-c, nagasai-t ,

## Slide 6: 目录 Content
2
项目规划 Project Schedule
1
项目范围 Project Scope
3
项目团队Project Team
6
项目沟通-工具 Project Communication- Tools
5
项目沟通 Project Communication
项目组织 Project Organization
4
7
角色与职责 Project R&R

## Slide 7: 项目组织 Project Organization
IT
Project Sponsors
Project Group Management Office (PMO)
Project Director: Chandra (IT)
Project Manager-APC: Chandra (IT)
Core Business Process Group
Business Department
BPO : Uday-G ,
KU(1) : Ramaiah-b
BPO: business process owner
APC IT
Team Leader : Syamsundar-r-r
Project Developers : Manohar-g ,
Premika-s
Steering Committee
Sivakumar-pc , nagasai-t ,
Ramaiah-b , Chandra-k
Production Department
FG Department
BPO : Sailaja-y
KU(2) : siva-c , nagasai-t
BPO : Kumar-KSS
KU(1) : Chandra-k

## Slide 8: 角色与职责 Project R&R
Project Sponsors
Steering Committee
PMO
Core Biz Process Group
Biz Process Owner/Leader
Provide project resources
Coordinate project resources
Provide guidance
Key decision making
Manage project resources
Manage and control project plans and changes
Support the project team and ensure that goals are achieved
Submit key problems to the steering committee
Analyze requirements and output solutions
Development and tests
Execute and complete tasks according to plan
Submit project results
Confirm the blueprint design and change points
Coordinate key users resources

## Slide 9: 项目沟通 Project Communication
Type of Communication | Frequency | Purpose and Content | Output | Originator | Attendees / Senders
Weekly Report | Every Friday till project go-live APC 16:00-16:30 | Email report on project progress | Project Progress Report | IT | IT Members
Weekly meeting – Project | Every Saturday till project go-live | Report on the progress of the project Next work plan Where help is needed | Meeting Minutes | IT | Biz , Production , FG Team members

## Slide 10: 项目沟通-工具 Project Communication- Tools
Email
WhatsApp

## Slide 11: Thanks 態度決定高度 Attitude is altitude