## Project Tracking
序号 No | 阶段 Phase | 工作事项 Item | 具体内容 Detailed content | 负责人 Owner | 参与人 Participants | 预计开始 日期 Plan Start | 预计完成 日期 Due day | 实际完成 日期 Finish data | 状态 Status | 涉及部门 Related department | 涉及人数 Related qty | 投入说明 Input description | 投入人天 Input MDs | 备注 Remark
1 | 准备 Preparation | 高阶需求调研 High-level demands study | 沟通梳理高阶需求 Communicate and output high-level requirements | ShyamSundar-r Manohar-G | ShyamSundar-r Manohar,Premika, Kumar,uday | 2025-01-15 | 2025-01-21 | 2025-01-21 | Close | IT/Planning , Production | 4 | Around 5 hours per day | 6 |  | 224
2 | 准备 Preparation | 项目立项 Project initiation | 项目立项-资料填写 Project initiation-data fill in | Manohar-G | Premika | 2025-01-16 | 2025-01-17 | 2025-01-21 | Close | IT | 1 | Around 4 hours per day | 1
3 | 准备 Preparation | 项目启动 Kick-off | Project Kick Off meeting hosted for all reated departments | Manohar-G | Chandrasekhar-v ShyamSundar-r Manohar-G Premika-s Nagarjuna , Srinu | 2025-01-22 | 2025-01-22 | 2025-01-23 | Close | IT/Planning , Production | 5 | Around 2 hours per day | 1.25
4 | 蓝图 Blueprint | 业务蓝图设计 Business blueprint design & IT总规划输出 IT Master Plan | Based on the business(FG,Business) blueprint, design IT solutions. | ShyamSundar-r,Manohar | Manohar,Premika Nagarjuna , Srinu | 2025-01-23 | 2025-01-28 | 2025-01-28 | Close | IT/Planning , Production | 4 | Around 5 hours per day | 9.3
4 | 蓝图 Blueprint | 蓝图汇报 Blueprint review | 针对蓝图设计成果进行汇报，确认蓝图设计方案 Report and finalize blueprint solution | manohar,premika ShyamSundar-r | ShyamSundar-r Manohar,Premika Nagarjuna , Srinu | 2025-01-29 | 2025-01-29 | 2025-02-08 | Close | IT/Planning , Production | 5 | Around 3 hours per day | 1.5
4 | 蓝图 Blueprint | IT功能清单输出 IT FunctionList Output |  | manohar, ShyamSundar-r | ShyamSundar-r Manohar,Premika | 2025-01-30 | 2025-02-05 | 2025-02-05 | Close | IT/Planning , Production | 3 | Around 5 hours per day | 11.25
5 | 实现 Realization | 功能说明书输出 Function specification output | Output IT function specification | Manohar-G | ShyamSundar-r,Manohar,Premika | 2025-02-06 | 2025-02-10 | 2025-02-10 | Close | IT | 3 | Around 3 hours per day | 5.6
6 | 实现 Realization | 功能开发 Function development |  | Manohar-G | Manohar,premika | 2025-02-11 | 2025-06-28 | 2025-06-28 | Close | IT | 2 | Around 4 hours per day | 114
7 | 实现 Realization | 单元测试-IT Unit test-IT |  | Manohar-G |  | 2025-06-30 | 2025-07-10 | 2025-07-02 | Close | IT | 2 | Around 3 hours per day | 7.5
8 | 实现 Realization | 单元测试-业务 Unit test-Biz |  | Premika,manohar | Nagarjuna , srinu | 2025-07-11 | 2025-07-15 | 2025-07-15 | Close | Planning , Production | 2 | Around 3 hours per day | 6
9 | 实现 Realization | 关键用户培训 Key user training |  | Manohar - G | Manohar,Premika,Nagarjuna , Srinu | 2025-07-15 | 2025-07-17 | 2025-07-17 | Close | IT/Planning , Production | 4 | Around 4 hours per day | 8
10 | 实现 Realization | 集成测试 System integration test |  | Manohar | ShyamSundar,Manohar,Premika | 2025-07-18 | 2025-07-21 | 2025-07-21 | Close | IT | 3 | Around 4 hours per day | 7.5
11 | 实现 Realization | 用户接受测试 User acceptance test |  | Nagarjuna | Nagarjuna , srinu | 2025-07-22 | 2025-07-26 | 2025-07-26 | Close | Planning , Production | 2 | Around 4 hours per day | 4
12 | 蓝图到上线前准备 Blueprint to Final Prep. | 主数据准备 Master data preparation |  | Manohar-g | Manohar-g , ShyamSundar | 2025-01-21 | 2025-06-21 | 2025-06-21 | Close | IT | 2 | Around 0.5 hours per day | 16
13 | 上线前准备 Final Preparation | 压力测试 Pressure test |  | Manohar-g | Manohar-g , ShyamSundar | 2025-07-28 | 2025-07-29 |  | Cancel | IT | 2 | Around 4 hours per day | 1
14 | 上线前准备 Final Preparation | 回归测试 Regression test |  | Manohar-g | Manohar-g , ShyamSundar | 2025-07-30 | 2025-07-31 | 2025-07-31 | Close | IT | 2 | Around 4 hours per day | 1
15 | 上线前准备 Final Preparation | 权限设计 Rights design |  | Manohar-g | Manohar-g , ShyamSundar | 2025-08-01 | 2025-08-02 | 2025-08-02 | Close | IT | 2 | Around 4 hours per day | 1
16 | 上线前准备 Final Preparation | 权限测试 Rights test |  | Manohar-g | Nagarjuna | 2025-08-04 | 2025-08-05 | 2025-08-05 | Close | IT | 2 | Around 4 hours per day | 1
17 | 上线前准备 Final Preparation | 权限分配 Rights assignment |  | Manohar-g | Manohar-g , ShyamSundar , Uday,Kumar | 2025-08-06 | 2025-08-07 | 2025-08-07 | Close | IT | 4 | Around 4 hours per day | 1
18 | Final Preparation | 上线准备情况汇报 Go-live Readiness Review |  | Manohar | Premika,Manohar ShyamSundar-r | 2025-08-07 | 2025-08-09 | 2025-08-08 | Close | IT | 3 | Around 3 hours per day | 4.5
19 | Final Preparation | 上线切换 Move To Production |  | Manohar | Premika,Manohar | 2025-08-11 | 2025-08-12 | 2025-08-12 | Close |  | 2 | Around 4 hours per day | 3
20 | 上线后支持 Post-production Support | 上线 Go-live |  | Manohar | Manohar,Premika | 2025-08-13 | 2025-08-13 | 2025-08-13 | Close | IT | 2 | Around 1 hours per day | 0.5
21 | PPS | 上线后问题追踪处理 PPS issues tracking and handling && 使用情况追踪 System utilization tracking |  | Manohar | ShyamSundar, Manohar,Premika | 2025-08-14 | 2025-08-29 | 2025-08-26 | Close | IT | 3 | Around 3 hours per day | 12
22 | PPS | 项目退出 Project exit |  | Manohar | Manohar | 2025-08-30 | 2025-08-30 | 2025-09-01 | Close | IT | 1 | Around 1 hours per day | 0.1