## Sheet1
Function names | Owner | FS plan to finish | FS actual finish date | Dev owner | Dev plan to start | Dev plan to finish | Dev actual start date | Dev actual finish date | IT Tester | IT test plan to finish | Test actual finish date | Biz Tester | Test plan to finish | Test actual finish date | Remark | Status
Project Setup | Manohar-g | 2025-02-06 | 2025-02-06 | Manohar-g | 2025-02-15 | 2025-02-28 | 2025-02-05 | 2025-02-08 | ShyamSundar-r | 2025-02-17 | 2025-02-17 | Naga-Planning | 2025-03-01 | 2025-03-01 |  | Completed
Order Report | Manohar-g | 2025-02-06 | 2025-02-06 | Manohar-g | 2025-03-01 | 2025-03-08 | 2025-02-10 | 2025-03-07 | ShyamSundar-r | 2025-03-05 | 2025-03-05 | Naga-Planning | 2025-03-10 | 2025-03-10 |  | Completed
BOM Report | Manohar-g | 2025-02-07 | 2025-02-07 | Manohar-g | 2025-03-10 | 2025-03-19 | 2025-03-08 | 2025-03-18 | ShyamSundar-r | 2025-03-14 | 2025-03-14 | Naga-Planning | 2025-03-22 | 2025-03-22 |  | Completed
Warehouse Report | Manohar-g | 2025-02-07 | 2025-02-07 | Manohar-g | 2025-03-20 | 2025-03-21 | 2025-03-19 | 2025-03-21 | ShyamSundar-r | 2025-03-24 | 2025-03-24 | Naga-Planning | 2025-03-26 | 2025-03-26 |  | Completed
Cutting Report in Production Report | Manohar-g | 2025-02-08 | 2025-02-08 | Manohar-g | 2025-03-22 | 2025-03-24 | 2025-03-22 | 2025-03-24 | ShyamSundar-r | 2025-03-25 | 2025-03-25 | Srinu | 2025-03-29 | 2025-03-29 |  | Completed
Stitching Report in Production Report | Manohar-g | 2025-02-08 | 2025-02-08 | Manohar-g | 2025-03-25 | 2025-03-27 | 2025-03-25 | 2025-03-27 | ShyamSundar-r | 2025-03-29 | 2025-03-29 | Srinu | 2025-04-01 | 2025-04-01 |  | Completed
Assembly an Packing Report in Production Report | Manohar-g | 2025-02-08 | 2025-02-08 | Manohar-g | 2025-03-28 | 2025-03-31 | 2025-03-28 | 2025-03-29 | ShyamSundar-r | 2025-03-31 | 2025-03-29 | Srinu | 2025-04-02 | 2025-04-02 |  | Completed
FG Report | Manohar-g | 2025-02-10 | 2025-02-10 | Manohar-g | 2025-04-02 | 2025-04-14 | 2025-04-02 | 2025-04-14 | ShyamSundar-r | 2025-04-15 | 2025-04-16 | Srinu | 2025-04-17 | 2025-04-17 |  | Completed
Escalations | Manohar-g | 2025-02-10 | 2025-02-10 | Manohar-g | 2025-04-16 | 2025-05-01 | 2025-04-16 | 2025-05-02 | ShyamSundar-r | 2025-05-03 | 2025-05-03 | Naga-Planning | 2025-05-08 | 2025-05-05 |  | Completed
Shipment Report | Manohar-g | 2025-02-10 | 2025-02-10 | Manohar-g | 2025-05-02 | 2025-05-14 | 2025-05-03 | 2025-05-20 | ShyamSundar-r | 2025-05-16 | 2025-05-23 | Srinu | 2025-05-19 | 2025-05-24 |  | Completed
Material Availability | Manohar-g | 2025-05-24 | 2025-05-24 | Manohar-g | 2025-05-26 | 2025/06/07 | 2025-05-26 | 2025-06-06 | ShyamSundar-r | 2025-06-14 | 2025-06-14 | Naga-Planning | 2025-06-17 | 2025-06-14 |  | Completed
Planning Schedule Suggestion | Manohar-g | 2025-05-24 | 2025-05-24 | Manohar-g | 2025/06/09 | 2025/06/28 | 2025-06-09 | 2025-06-28 | ShyamSundar-r | 2025-07-02 | 2025-07-02 | Naga-Planning | 2025-07-10 | 2025-07-10 |  | Completed