## Sheet1
序号 No. | 功能编号 Function no. | 说明 Description | 测试输入数据 Input data | 测试结果 Test Result | 测试责任人 Owner | 是否通过 Pass or not | 备注 Remark | 测试完成时间 Complete date | 签字确认 Sign-off
1 | Order Report | 1. This function Visualize the order article quantity based on CRD , PO , ARTICLE 2 . Visulaize the order details in PO tracking report | CRD : 2025/06/30 PO : 0900237611&1. Article( Optional ) | Test result is OK | Nagarjuna | Pass |  | 2025-03-10
2 | BOM Report | Visulaization of bom status and bom details | PO : 0900237611&1. Article( Optional ) | Test result is OK | Nagarjuna | Pass |  | 2025-03-22
3 | Warehouse Report | Visualization of material status for each po or so and send automatic alerts to planning department if material not | SO : 1000237027 PO : 0900907627&1 Material : 4030214312 | Test result is OK | Nagarjuna | Pass |  | 2025-03-26
4 | Cutting Report in Production Report | 1 . Cutting dates in po tracking report 2 . Cutting overal status and output and size wise status | CRD : 2025/06/30 PO : 0900237611&1. Article( Optional ) | Test result is OK | Srinu | Pass |  | 2025-03-29
5 | Stitching Report in Production Report | 1 . Stitching dates in po tracking report 2 . Stiching overal status and output and size wise status | CRD : 2025/06/30 PO : 0900237611&1. Article( Optional ) | Test result is OK | Srinu | Pass |  | 2025-04-01
6 | Assembly and Packing Report in Production Report | 1 . Assembly dates in po tracking report 2 . Assembly and packing overal status and output and size wise status | CRD : 2025/06/30 PO : 0900237611&1. Article( Optional ) | Test result is OK | Srinu | Pass |  | 2025-04-02
7 | FG Report | 1 . Visualize FG Status and FG Time Lines and FG Output for each PO | CRD : 2025/06/30 PO : 0900237611&1. Article( Optional ) | Test result is OK | Srinu | Pass |  | 2025-04-17
8 | Escalations | 1 . Escalation through whatsapp to every person for material issues and other issue 2. Send automatic escaltion to planning department about cutting stop lines | N/A | Test result is OK | Nagarjuna | Pass |  | 2025-05-05
10 | Shipment Report | 1. Visualization of shipment Article qty 2 . Visualization of shipment qty , shipment date , shipment status by PO wise 3 . Times lines for shipment 4 . PO completion | CRD : 2025/06/30 PO : 0900237611&1. Article( Optional ) | Test result is OK | Srinu | pass |  | 2025-05-24
11 | Material Availability | 1. Visualization of Material avialability status 2 . Visulize material available Pos 3 . Visulize material not available Pos 3 . Visualize bom and uper available and not avialable pos | Week : Material Status : Bottom Status : Upper Status : SO: | Test result is OK | Nagarjuna | pass |  | 2025-06-14
12 | Planning Schedule Suggestion | 1 . Identifing cutting stop lines 2 . Identifying Stitching stop lines 3 . Identifying assembly stop lines 4 . Give suggestion to the planning department | Week : Material Status : Bottom Status : Upper Status : SO: | Test result is OK | Nagarjuna | pass |  | 2025-07-10