## Slide 1: End to End Decision Making System Project Go-live Readiness Review
Project team
2025/08/09
e万行动，e-Apache, one Apache

## Slide 2: 目录 Content
项目范围 Project Scope（必选 Required）
项目效益 Project Benefit （必选 Required）
项目整体状态 Project Status Overview（必选 Required）
变更汇总说明 Change Request Summary （取决于实际情况 Depends）
上线准备检核表Go-live Readiness Checklist（必选 Required）
上线后支持规划 Post-production Support Plan（必选 Required）
上线后效益追踪规划 Post-production Benefit Tracking Plan（可选 Optional ）
问题与风险 Problems & Risks （取决于实际需要 Depends on actual needs）
上线决策 Go-live Decision （必选 Required）

## Slide 3: 项目范围 Project Scope
序号 No. | 类别 Category | 范围内 Scope-in | 范围外 Scope-out | 备注 Remark
1 | 公司 Company | APACHE 5001 |  | Later Will Implement in T2 Factories.
2 | 模块 Modules | End To End Decision Making System |  | 
3 | 系统系统System | Dashboard Visualization Data Visualization based on child article in BOM Data visualization for purchase based on article and material components Output Quantities data visualization for Production Output Quantities data visualization for finished goods and shipment Accessing Permissions Module based Permissions are given Identify Identify the cutting stoppage lines before 3 days and escalate issues to warehouse department for material. | It Avoids duplicate data. It avoids large time for data tracking. | 

## Slide 4: 项目收益 Project Benefit
Hard Saving : End to End Decision making system Can Saves 1 Hours Per Working Day For Each Person.
Total Mds Saved: 468 Mds (4 Staff *1 Hour Per Day *26 Working Days Per Month*12 Months*3 Years/8 Hours Per Day)
Hard Saving Amount: USD $5,054.40

## Slide 5: 目录 Content
项目范围 Project Scope（必选 Required）
项目效益 Project Benefit （必选 Required）
项目整体状态 Project Status Overview（必选 Required）
上线准备检核表Go-live Readiness Checklist（必选 Required）
上线后支持规划 Post-production Support Plan（必选 Required）
上线后效益追踪 Post-production Benefit Tracking Plan （可选 Optional ）
问题与风险 Problems & Risks （取决于实际需要 Depends on actual needs）
上线决策 Go-live Decision （必选 Required）

## Slide 6: Project Status Overview
Close
Delay
On-going
Not start
We are here
08/13 Go-live
01/21 PI
08/13 Go-live
PI
01/21 Close
蓝图Blueprint
02/08 Completed
01/23 KO &02/08
Blueprint Review
08/09 Project sign-off
08/09 Project sign-off
KO Prep
01/23 Completed
01/23 Kick-off
01/20
01/24
01/25
01/27
02/28
GRR：2025/08/09
06/30
Project Exit：2025/08/30
Realization ：2025/07/26 Completed
04/16
05/01
05/15
06/01
06/15

## Slide 7: 上线准备检核表Go-live Readiness Checklist-01
序号 No. | 类别 Category | 检核项 Check list | 责任人 Owner | 目标完成 Target date | 实际完成 Actual finish | 状态 Status | 备注Remark
1 | 蓝图BP | 业务解决方案签核确认Business solution sign-off |  |  |  | Close | 
2 | 蓝图BP | IT解决方案签核确IT solution sign-off |  |  |  | Close | 
3 | 培训Training | 关键用户都已经参加培训All key users attend training |  |  |  | Close | 
4 | 培训Training | 最终用户都已经参加培训All end users attend training |  |  |  | Close | 
5 | 培训Training | 最终用户通过培训检验 All end users pass training test/exam |  |  |  | Close | 
6 | 培训Training | 已经制作系统操作手册和相关的管理制度 SOPs and related management files have been output |  |  |  | Not applicable | 
7 | 测试Test | 已经进行SIT测试，测试结果满足上线需求 SIT pass and fulfill go-live requirements |  |  |  | Close | 
8 | 测试Test | 已经进行了UAT测试，测试结果满足上线需求 UAT pass and fulfill go-live requirements |  |  |  | Close | 
9 | 测试Test | 已进行压力测试，测试结果满足上线需求 Performance test pass and fulfill go-live requirements |  |  |  | Close | 
10 | 测试Test | 已进行回归测试，测试结果满足上线需求 Regression test pass and fulfill go-live requirements |  |  |  | Close | 
11 | 测试Test | 已进行用户权限测试，测试结果满足上线需求 Rights test pass and fulfill go-live requirements |  |  |  | Close | 

## Slide 8: 上线准备检核表Go-live Readiness Checklist-01
序号 No. | 类别 Category | 检核项 Check list | 责任人 Owner | 目标完成 Target date | 实际完成 Actual finish | 状态 Status | 备注Remark
12 | 上线前准备 Final Prep. | 上线切换策略已经输出并达成共识 MTP strategy output and aligned |  |  |  | Not applicable | 
13 | 上线前准备 Final Prep. | 上线切换承诺书签署确认 Move-to-production Commitment file sign-off |  |  |  | Not applicable | 
14 | 上线前准备 Final Prep. | 上线切换任务规划输出 Move to production planoutput |  |  |  | Not applicable | 
15 | 上线前准备 Final Prep. | 网络正常，服务器和客户端的软件已经安装并测试可以正常使用 Network is OK, the server and client software have been installed and tested and can be used normally |  |  |  | Close | 
16 | 上线前准备 Final Prep. | 相关用户的账号权限在正式系统都已经建立完毕 The accounts and rights of relevant users have been established. |  |  |  | Close | 
17 | 上线前准备 Final Prep. | 基础数据准备完毕，并已经录入正式环境，且由用户确认准确 Master data has been prepared and entered into the production database, and confirmed by the user. |  |  |  | Close | 
18 | 上线前准备 Final Prep. | 已经明确上线之后的问题反馈和解决流程（PPS Plan） The problem feedback and fixing process after the go-live has been clarified (PPS Plan) |  |  |  | Close | 
19 | 上线前准备 Final Prep. | 各阶段主要项目输出文档均已记录并上传 The documents of each phase have been recorded and uploaded |  |  |  | Close | 

## Slide 9: 目录 Content
项目范围 Project Scope（必选 Required）
项目效益 Project Benefit （必选 Required）
项目整体状态 Project Status Overview（必选 Required）
变更汇总说明 Change Request Summary （取决于实际情况 Depends）
上线准备检核表Go-live Readiness Checklist（必选 Required）
上线后支持规划 Post-production Support Plan（必选 Required）
问题与风险 Problems & Risks （取决于实际需要 Depends on actual needs）
上线决策 Go-live Decision （必选 Required）

## Slide 10: 上线后支持规划 Post-production Support Plan
First level support: contact key users to handle problems
Second level support: Tracking real-time data based on reports and guiding departments to maintain perfect data.
Post-production support plan: 1 month after go-live

## Slide 11: 目录 Content
项目范围 Project Scope（必选 Required）
项目效益 Project Benefit （必选 Required）
项目整体状态 Project Status Overview（必选 Required）
变更汇总说明 Change Request Summary （取决于实际情况 Depends）
上线准备检核表Go-live Readiness Checklist（必选 Required）
上线后支持规划 Post-production Support Plan（必选 Required）
效益追踪规划 Benefit Tracking Plan（可选 Optional ）
问题与风险 Problems & Risks （取决于实际需要 Depends on actual needs）
上线决策 Go-live Decision （必选 Required）

## Slide 12: 上线决策 Go-live Decision
YES
NO

## Slide 13: Thanks 態度決定高度 Attitude is altitude